## Project Planner
Project Plan
| Legend for chart is as follows: | [8 empty] | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
TIMELINE (BY MAN HOURS)
| ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | Inception | [11 empty] | Elaboration | [27 empty] | Construction |  |  |  |  | Transition
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50
| Setup of TortoiseSVN | 1 | 2 | 1 | 3 | 100%
| Business Use Case | 1 | 2 | 2 | 3 | 100%
| SRS Section 1 -2 | 1 | 10 | 2 | 9 | 100%
| Use Case Diagrams | 1 | 6 | 1 | 5 | 100%
| Gantt Chart | 1 | 4 | 3 | 5 | 100%
| Activity Workflow Diagrams | 1 | 5 | 2 | 4 | 100%
| Sequence Diagrams | 5 | 7 | 4 | 6 | 100%
| Class Component Diagram | 5 | 7 | 4 | 6 | 100%
| SRS Section 3 - 4 | 10 | 20 | 9 | 17 | 100%
| Risks and Countermeasure | 12 | 5 | 12 | 4 | 100%
| SRS Section 5-6 | 30 | 15 | 26 | 14 | 100%
| Update of Diagrams | 20 | 6 | 17 | 6 | 100%
| Gantt Chart Update | 15 | 2 | 15 | 1 | 100%
| Preparation of Powerpoint and Report | 30 | 5 | 30 | 4 | 100%
Construction and Transition phases have not been planned in depth yet.